## Sheet1
Activity | Item | Task | Room | Location | Notes | Start Date | End Date | Status | Workdays
Civil Work | Wall | New | Toilet 2 | Westwall |  | 2025-03-01 | 2025-03-10 |  | 8
Civil Work | Wall extended outward | Brickwork | Office / Bedroom 4 | South |  | 2025-03-01 | 2025-03-10 |  | 8
Civil Work | Window gap filled | Brickwork | Bedroom 1 | West |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Front Grill | Discard | Sitout | South |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Rack/cubboard | Discard | Bedroom 2 | West |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Window | Discard | Bedroom 2 | South |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Wall | Demolish | Toilet 2 | Westwall |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Windows | Resize | Kitchen | East |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Windows | Resize | Pantry | East |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Cornice | discard | Dining/Living | All |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Handrail | discard | Sitout | East |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Wall | Demolish | Office / Bedroom 4 | South |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Showcase | Discard | Living Room | Westwall |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Stairs | Discard | Dining Room |  |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Toilet | Demolish | Outside | North |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Slab and Bubboards | Discard | Kitchen / Pantry | South/West/East/North |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Partial wall | Demolish | Kitchen | North |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Door | Discard | Kitchen | North |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Doorway | Demolish | Kitchen | West |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Door | Discard | Kitchen | West |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Grill and wall | Discard | Bedroom 1 | North |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Parapet wall and sunshade | Discard | Bedroom 3 |  |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Parapet wall and sunshade | Discard | Roof |  |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Stairs | Discard | Terrace |  |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Popcorn grooves | Demolish | outer walls |  |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Floors and bathroom tiles | Demolish | All |  |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Sitout Grill | Discard | Office / Bedroom 4 | South |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | wall near window opened | Demolish | Bedroom 1 | West |  | 2025-03-01 | 2025-03-10 |  | 8
Demolition Work | Door | Move | Maid's Room | Hallway |  | 2025-03-01 | 2025-03-10 |  | 8
Civil Work | Window | Resize | Bedroom 2 | South |  | 2025-03-11 | 2025-03-31 |  | 18
Civil Work | Door | New | Bedroom 2 | Veranda |  | 2025-03-11 | 2025-03-31 |  | 18
Civil Work | Door | Reposition | Toilet 1 | Bedroom 1 |  | 2025-03-11 | 2025-03-31 |  | 18
Civil Work | Door | Reposition | Toilet 4 | Bedroom 3 |  | 2025-03-11 | 2025-03-31 |  | 18
Civil Work | Partition | brick and woodwork | Living room |  |  | 2025-03-11 | 2025-03-31 |  | 18
Civil Work | Kitchen |  |  |  |  | 2025-03-11 | 2025-03-31 |  | 18
Civil Work | Wall | Brickwork | Bathroom 3 | South |  | 2025-03-11 | 2025-03-31 |  | 18
Civil Work | Parapet wall | Brickwork |  |  |  | 2025-03-11 | 2025-03-31 |  | 18
Civil Work | Veranda | Cement | Bedroom 2 | Outside |  | 2025-03-11 | 2025-03-31 |  | 18
Civil Work | Walls | Brickwork | Bedroom 3 | South / North |  | 2025-03-11 | 2025-03-31 |  | 18
Civil Work | Wall | Brickwork | Toilet 4 | East |  | 2025-03-11 | 2025-03-31 |  | 18
Civil Work | Stairs | Brick and Metal work | Living Room |  |  | 2025-03-11 | 2025-03-31 |  | 18
Civil Work | Handrail |  | Library |  |  | 2025-03-11 | 2025-03-31 |  | 18
Civil Work | Circular stair | Metal work | Terrace |  |  | 2025-03-11 | 2025-03-31 |  | 18
Civil Work | wall | Brickwork | Bedroom 1 | Study/Seat Area |  | 2025-03-11 | 2025-03-31 |  | 18
Civil Work | floor extended | New | Toilet 2 | Shower |  | 2025-03-11 | 2025-03-31 |  | 18
Civil Work | Veranda | Cement | Bedroom 2 | Outside |  | 2025-03-11 | 2025-03-31 |  | 18
Civil Work | Backyard stairs | Brickwork | Dining / Kitchen | Outside |  | 2025-03-11 | 2025-03-31 |  | 18
Civil Work | Door | Replace | Maid's Room | Entrance |  | 2025-03-11 | 2025-03-31 |  | 18
Civil Work | Steel Roof | Fabrication | Veranda | Bedroom 2 |  | 2025-03-11 | 2025-03-31 |  | 18
Civil Work | Handrail | Fabrication | Patio Extension | Patio |  | 2025-03-11 | 2025-03-31 |  | 18
Door/Window Change | Window | New | Bedroom 2 | South |  | 2025-03-11 | 2025-03-25 |  | 13
Door/Window Change | Door | New | Bedroom 2 | Veranda |  | 2025-03-11 | 2025-03-25 |  | 13
Door/Window Change | Window | New | Toilet 2 | Westwall |  | 2025-03-11 | 2025-03-25 |  | 13
Door/Window Change | Door | New | Toilet 2 | Westwall |  | 2025-03-11 | 2025-03-25 |  | 13
Door/Window Change | Windows | New | Bedroom 1 | West | 2 | 2025-03-11 | 2025-03-25 |  | 13
Door/Window Change | Windows | New | Bedroom 1 | North |  | 2025-03-11 | 2025-03-25 |  | 13
Door/Window Change | Door | New | Toilet 1 | Bedroom 1 |  | 2025-03-11 | 2025-03-25 |  | 13
Door/Window Change | Door | New | Dining Room | Backyard |  | 2025-03-11 | 2025-03-25 |  | 13
Door/Window Change | Windows | Replace | Pantry | North |  | 2025-03-11 | 2025-03-25 |  | 13
Door/Window Change | Windows | Replace | Stairwell | North |  | 2025-03-11 | 2025-03-25 |  | 13
Door/Window Change | Door | New | Toilet 3 | Maid's Room | double doors | 2025-03-11 | 2025-03-25 |  | 13
Door/Window Change | Door | New | Toilet 4 | Bedroom 3 |  | 2025-03-11 | 2025-03-25 |  | 13
Door/Window Change | Door | New | Toilet 5 | Hallway |  | 2025-03-11 | 2025-03-25 |  | 13
Door/Window Change | Door | Reposition | Bedroom 3 | Hallway |  | 2025-03-11 | 2025-03-25 |  | 13
Door/Window Change | Window | Resize | Library | North |  | 2025-03-11 | 2025-03-25 |  | 13
Door/Window Change | Doors | New | Library | Patio |  | 2025-03-11 | 2025-03-25 |  | 13
Door/Window Change | Doors | New | Conference | Terrace |  | 2025-03-11 | 2025-03-25 |  | 13
Door/Window Change | Windows | New | Office / Bedroom 4 | East |  | 2025-03-11 | 2025-03-25 |  | 13
Door/Window Change | Windows | New | Office / Bedroom 4 | South/East |  | 2025-03-11 | 2025-03-25 |  | 13
Door/Window Change | Windows | New | Bedroom 3 | West/North |  | 2025-03-11 | 2025-03-25 |  | 13
Electrical | [5 empty] | 2025-04-01 | 2025-04-15 |  | 13
Electrical | Inverter | New |  |  |  | 2025-04-01 | 2025-04-15 |  | 13
Flooring, Tiling, Sealing | [5 empty] | 2025-04-01 | 2025-04-20 |  | 17
Plumbing | [5 empty] | 2025-04-01 | 2025-04-15 |  | 13
Bathroom Tiles | Floor |  | Toilet 1 |  |  | 2025-04-15 | 2025-04-20 |  | 5
Bathroom Tiles | Walls |  | Toilet 1 |  |  | 2025-04-15 | 2025-04-20 |  | 5
Bathroom Tiles | Floor |  | Toilet 2 |  |  | 2025-04-15 | 2025-04-20 |  | 5
Bathroom Tiles | Walls |  | Toilet 2 |  |  | 2025-04-15 | 2025-04-20 |  | 5
Bathroom Tiles | Floor |  | Toilet 3 |  |  | 2025-04-15 | 2025-04-20 |  | 5
Bathroom Tiles | Walls |  | Toilet 3 |  |  | 2025-04-15 | 2025-04-20 |  | 5
Bathroom Tiles | Floor |  | Toilet 4 |  |  | 2025-04-15 | 2025-04-20 |  | 5
Bathroom Tiles | Walls |  | Toilet 4 |  |  | 2025-04-15 | 2025-04-20 |  | 5
Bathroom Tiles | Floor |  | Toilet 5 |  |  | 2025-04-15 | 2025-04-20 |  | 5
Bathroom Tiles | Walls |  | Toilet 5 |  |  | 2025-04-15 | 2025-04-20 |  | 5
Carpentary Work | Clothing Cabinets | New | Bedroom 2 | South |  | 2025-05-01 | 2025-05-15 |  | 13
Carpentary Work | Clothing Cabinet | New | Bedroom 1 | South |  | 2025-05-01 | 2025-05-15 |  | 13
Carpentary Work | Liquor Cabinet | New | Bedroom 1 | Sitting Area |  | 2025-05-01 | 2025-05-15 |  | 13
Carpentary Work | Writing Desk | New | Bedroom 1 | Study Area |  | 2025-05-01 | 2025-05-15 |  | 13
Carpentary Work | Clothing Cabinet | New | Bedroom 3 | South |  | 2025-05-01 | 2025-05-15 |  | 13
Carpentary Work | Cabinet | New | Toilet 1 |  |  | 2025-05-01 | 2025-05-15 |  | 13
Carpentary Work | Cabinet | New | Toilet 2 |  |  | 2025-05-01 | 2025-05-15 |  | 13
Carpentary Work | Cabinet | New | Toilet 3 |  |  | 2025-05-01 | 2025-05-15 |  | 13
Carpentary Work | Cabinet | New | Toilet 4 |  |  | 2025-05-01 | 2025-05-15 |  | 13
Carpentary Work | Cabinet | New | Toilet 5 |  |  | 2025-05-01 | 2025-05-15 |  | 13
Carpentary Work | Cabinets | New | Kitchen/Pantry |  |  | 2025-05-01 | 2025-05-15 |  | 13
Plastering | [5 empty] | 2025-05-10 | 2025-05-13 |  | 3
Bathroom Fixures | Glass shower door | New | Toilet 1 |  |  | 2025-05-15 | 2025-05-30 |  | 14
Bathroom Fixures | Shower Hardware | New | Toilet 1 |  |  | 2025-05-15 | 2025-05-30 |  | 14
Bathroom Fixures | Washbasin and Hardware | New | Toilet 1 |  |  | 2025-05-15 | 2025-05-30 |  | 14
Bathroom Fixures | Pressure Pump | New |  |  |  | 2025-05-15 | 2025-05-30 |  | 14
Bathroom Fixures | Central Water Heating Unit | New |  |  |  | 2025-05-15 | 2025-05-30 |  | 14
Bathroom Fixures | Glass shower door | New | Toilet 2 |  |  | 2025-05-15 | 2025-05-30 |  | 14
Bathroom Fixures | Shower Hardware | New | Toilet 2 |  |  | 2025-05-15 | 2025-05-30 |  | 14
Bathroom Fixures | Washbasin and Hardware | New | Toilet 2 |  |  | 2025-05-15 | 2025-05-30 |  | 14
Bathroom Fixures | Shower Hardware | New | Toilet 3 |  |  | 2025-05-15 | 2025-05-30 |  | 14
Bathroom Fixures | Washbasin and Hardware | New | Toilet 3 |  |  | 2025-05-15 | 2025-05-30 |  | 14
Bathroom Fixures | Glass Shower door | New | Toilet 4 |  |  | 2025-05-15 | 2025-05-30 |  | 14
Bathroom Fixures | Shower Hardware | New | Toilet 4 |  |  | 2025-05-15 | 2025-05-30 |  | 14
Bathroom Fixures | Washbasin and Hardware | New | Toilet 4 |  |  | 2025-05-15 | 2025-05-30 |  | 14
Bathroom Fixures | Glass shower door | New | Toilet 5 |  |  | 2025-05-15 | 2025-05-30 |  | 14
Bathroom Fixures | Shower Hardware | New | Toilet 5 |  |  | 2025-05-15 | 2025-05-30 |  | 14
Bathroom Fixures | Washbasin and Hardware | New | Toilet 5 |  |  | 2025-05-15 | 2025-05-30 |  | 14
Painting and Putty Work | [5 empty] | 2025-05-15 | 2025-05-30 |  | 14
Waste Disposal | [5 empty] | 2025-05-30 | 2025-05-31 |  | 2
Deep Cleaning | [5 empty] | 2025-06-01 | 2025-06-02 |  | 1